## Project Velocita
PROJECT Velocita | [9 empty] | https://goo.gl/UTlQLz
| PROJECT DETAILS | [6 empty] | % DONE |  | PRIORITY KEY
STATUS | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION |  |  | Low
Work Name | [9 empty] | Medium
Items Detail | High | 2020-05-27 | 2020-06-18 | 21 | Task |  | items detail with many function in there is buy, bid and etc | 50% |  | High
Fee Wallet | High | 2020-06-01 | 2020-06-08 | 7 | Task |  | fee wallet sycn from app nft and admin to smartcontract token | 100%
Buy Transaction | High | 2020-06-05 | 2020-06-10 | 5 | Task |  | Buy Transaction there is 2 smart contract sycn. 1 smart contract token and 2 smart contract nft. after all total balance there is fee with plus payment for users to pay.all task will be show on admin | 60%
Bid Transaction | High | 2020-06-11 | 2020-06-15 | 4 | Task |  | there is 2 smart contract sycn. 1 smart contract token and 2 smart contract nft. after all total balance there is fee with plus payment for users to pay. for the bid. users creator must approve for another users bid. all task will be show on admin | 60%
Transfer NFT | High | 2020-06-13 | 2020-06-18 | 5 | Task |  | Transfer Nft from owner nft to another users in smart contract nft | 40%
History Item | High | 2020-06-19 | 2020-06-20 | 1 | Task |  | there is 2 hsistory, 1. bid and 2 history buy. | 90% | part 10% not finisih for trigger event bid and buy. when buy and bid done this part automatic done.
Stats Activity | Medium | 2020-06-21 | 2020-06-23 | 2 | Task |  | History activity from users. to inform activity like buy, transfer, and bid. | 0% | this part finish when Transfer NFT,buy and bid done
Stats Ranking | High | 2020-06-24 | 2020-06-29 | 5 | Task |  | Rank For item nft. | 0% | this part finish when buy and bid done
News | High | 2020-06-29 | 2020-07-02 | 3 | Task |  | News Info About Nft, you can create this new in admin. and show in page app nft | 0%
Note: All the task sycn app nft, admin and wallet. for wallet sycn to 2 smart contract